## Dashboard
Project Management Dashboard |  |  |  | 1-ene-23 to 28-feb-23
Project | Task | Manager | Start Date | End Date | Duration | Days Completed | Progress | Budget | Actual | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26
Cetus | Task 1 | Felipe | 2023-01-11 | 2023-01-19 | 7 | 7 | 100% | 380000 | 320000
| Task 10 | Thor | 2023-01-25 | 2023-02-03 | 8 | 3 | 37.5% | 320000 | 140000
| Task 2 | Karyn | 2023-01-16 | 2023-01-25 | 8 | 3 | 37.5% | 150000 | 60000
| Task 3 | Andy | 2023-01-18 | 2023-01-27 | 8 | 4 | 50% | 240000 | 120000
| Task 4 | Lucas | 2023-01-22 | 2023-01-31 | 7 | 2 | 28.57% | 232000 | 72000
| Task 5 | Thor | 2023-01-15 | 2023-01-26 | 9 | 3 | 33.33% | 100000 | 35000
| Task 6 | Felipe | 2023-01-17 | 2023-01-26 | 8 | 8 | 100% | 300000 | 225000
| Task 7 | Karyn | 2023-01-23 | 2023-02-01 | 8 | 2 | 25% | 150000 | 30000
| Task 8 | Andy | 2023-01-25 | 2023-01-31 | 5 | 0 | 0% | 150000 | 0
| Task 9 | Lucas | 2023-01-30 | 2023-02-07 | 7 | 2 | 28.57% | 50000 | 12000
Crux | Task 1 | Felipe | 2023-01-30 | 2023-02-07 | 7 | 3 | 42.86% | 150000 | 48000
| Task 2 | Karyn | 2023-02-06 | 2023-02-15 | 8 | 3 | 37.5% | 220000 | 88000
| Task 3 | Andy | 2023-02-06 | 2023-02-14 | 7 | 1 | 14.29% | 10000 | 1200
| Task 4 | Lucas | 2023-02-11 | 2023-02-24 | 10 | 3 | 30% | 400000 | 110000
| Task 5 | Thor | 2023-02-09 | 2023-02-17 | 7 | 2 | 28.57% | 320000 | 100000
| Task 6 | Felipe | 2023-02-05 | 2023-02-14 | 7 | 4 | 57.14% | 150000 | 80000
| Task 7 | Karyn | 2023-02-13 | 2023-02-17 | 5 | 1 | 20% | 100000 | 18000
Draco | Task 1 | Felipe | 2023-01-01 | 2023-01-05 | 4 | 4 | 100% | 450000 | 380000
| Task 10 | Thor | 2023-01-10 | 2023-01-17 | 6 | 0 | 0% | 450000 | 0
| Task 2 | Karyn | 2023-01-03 | 2023-01-12 | 8 | 4 | 50% | 75000 | 35000
| Task 3 | Andy | 2023-01-02 | 2023-01-09 | 6 | 2 | 33.33% | 110000 | 38000
| Task 4 | Lucas | 2023-01-06 | 2023-01-17 | 8 | 2 | 25% | 200000 | 52080
| Task 5 | Thor | 2023-01-05 | 2023-01-11 | 5 | 3 | 60% | 450000 | 275080
| Task 6 | Felipe | 2023-01-04 | 2023-01-13 | 8 | 2 | 25% | 320000 | 54000
| Task 7 | Karyn | 2023-01-10 | 2023-01-18 | 7 | 3 | 42.86% | 110000 | 55000
| Task 8 | Andy | 2023-01-08 | 2023-01-20 | 10 | 4 | 40% | 250000 | 134000
| Task 9 | Lucas | 2023-01-15 | 2023-01-24 | 7 | 2 | 28.57% | 80000 | 22000
Hydra | Task 1 | Felipe | 2023-01-24 | 2023-02-01 | 7 | 2 | 28.57% | 70000 | 28000
| Task 2 | Karyn | 2023-01-30 | 2023-02-08 | 8 | 3 | 37.5% | 100000 | 35000
| Task 3 | Andy | 2023-01-30 | 2023-02-08 | 8 | 2 | 25% | 50000 | 12000
| Task 4 | Lucas | 2023-02-05 | 2023-02-13 | 6 | 0 | 0% | 135000 | 0
| Task 5 | Thor | 2023-02-02 | 2023-02-10 | 7 | 2 | 28.57% | 220000 | 65000
Phoenix | Task 1 | Andy | 2023-02-12 | 2023-02-21 | 7 | 2 | 28.57% | 50000 | 15000
| Task 2 | Lucas | 2023-02-22 | 2023-02-28 | 5 | 2 | 40% | 160000 | 60000
| Task 3 | Thor | 2023-02-16 | 2023-02-24 | 7 | 3 | 42.86% | 280000 | 140000
| Task 4 | Felipe | 2023-02-12 | 2023-02-21 | 7 | 5 | 71.43% | 480000 | 305000
| Task 5 | Karyn | 2023-02-15 | 2023-02-21 | 5 | 2 | 40% | 100000 | 35000
| Task 6 | Andy | 2023-02-19 | 2023-02-24 | 5 | 2 | 40% | 120000 | 50000
| Task 7 | Lucas | 2023-02-25 | 2023-02-28 | 2 | 1 | 50% | 50000 | 25000
| Task 8 | Thor | 2023-02-22 | 2023-02-28 | 5 | 3 | 60% | 100000 | 55000
Grand Total | [7 empty] | 7832000 | 3329360
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Workings
Not Started | 3 | Values |  |  |  |  | Values |  |  |  | Scroll Bar
In Progress | 34 | Sum of Days Completed | 106 | Days Completed | 38.69% |  | Actual | 3329360 | Actual | 42.51% | 0
Completed | 3 | Sum of Duration | 274 | Days Remaining | 61.31% |  | Budget | 7832000 | Budget | 57.49%
Remaining | 37
Total Tasks | 40
[7 empty] | Actual | Budget
[6 empty] | Bar Chart | 3329360 | 7832000

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days Completed | Progress | Budget | Actual
Draco | Task 1 | Felipe | 2023-01-01 | 4 | 2023-01-05 | 4 | 100% | 450000 | 380000
Draco | Task 2 | Karyn | 2023-01-03 | 8 | 2023-01-12 | 4 | 50% | 75000 | 35000
Draco | Task 3 | Andy | 2023-01-02 | 6 | 2023-01-09 | 2 | 33.33% | 110000 | 38000
Draco | Task 4 | Lucas | 2023-01-06 | 8 | 2023-01-17 | 2 | 25% | 200000 | 52080
Draco | Task 5 | Thor | 2023-01-05 | 5 | 2023-01-11 | 3 | 60% | 450000 | 275080
Draco | Task 6 | Felipe | 2023-01-04 | 8 | 2023-01-13 | 2 | 25% | 320000 | 54000
Draco | Task 7 | Karyn | 2023-01-10 | 7 | 2023-01-18 | 3 | 42.86% | 110000 | 55000
Draco | Task 8 | Andy | 2023-01-08 | 10 | 2023-01-20 | 4 | 40% | 250000 | 134000
Draco | Task 9 | Lucas | 2023-01-15 | 7 | 2023-01-24 | 2 | 28.57% | 80000 | 22000
Draco | Task 10 | Thor | 2023-01-10 | 6 | 2023-01-17 | 0 | 0% | 450000 | 0
Cetus | Task 1 | Felipe | 2023-01-11 | 7 | 2023-01-19 | 7 | 100% | 380000 | 320000
Cetus | Task 2 | Karyn | 2023-01-16 | 8 | 2023-01-25 | 3 | 37.5% | 150000 | 60000
Cetus | Task 3 | Andy | 2023-01-18 | 8 | 2023-01-27 | 4 | 50% | 240000 | 120000
Cetus | Task 4 | Lucas | 2023-01-22 | 7 | 2023-01-31 | 2 | 28.57% | 232000 | 72000
Cetus | Task 5 | Thor | 2023-01-15 | 9 | 2023-01-26 | 3 | 33.33% | 100000 | 35000
Cetus | Task 6 | Felipe | 2023-01-17 | 8 | 2023-01-26 | 8 | 100% | 300000 | 225000
Cetus | Task 7 | Karyn | 2023-01-23 | 8 | 2023-02-01 | 2 | 25% | 150000 | 30000
Cetus | Task 8 | Andy | 2023-01-25 | 5 | 2023-01-31 | 0 | 0% | 150000 | 0
Cetus | Task 9 | Lucas | 2023-01-30 | 7 | 2023-02-07 | 2 | 28.57% | 50000 | 12000
Cetus | Task 10 | Thor | 2023-01-25 | 8 | 2023-02-03 | 3 | 37.5% | 320000 | 140000
Hydra | Task 1 | Felipe | 2023-01-24 | 7 | 2023-02-01 | 2 | 28.57% | 70000 | 28000
Hydra | Task 2 | Karyn | 2023-01-30 | 8 | 2023-02-08 | 3 | 37.5% | 100000 | 35000
Hydra | Task 3 | Andy | 2023-01-30 | 8 | 2023-02-08 | 2 | 25% | 50000 | 12000
Hydra | Task 4 | Lucas | 2023-02-05 | 6 | 2023-02-13 | 0 | 0% | 135000 | 0
Hydra | Task 5 | Thor | 2023-02-02 | 7 | 2023-02-10 | 2 | 28.57% | 220000 | 65000
Crux | Task 1 | Felipe | 2023-01-30 | 7 | 2023-02-07 | 3 | 42.86% | 150000 | 48000
Crux | Task 2 | Karyn | 2023-02-06 | 8 | 2023-02-15 | 3 | 37.5% | 220000 | 88000
Crux | Task 3 | Andy | 2023-02-06 | 7 | 2023-02-14 | 1 | 14.29% | 10000 | 1200
Crux | Task 4 | Lucas | 2023-02-11 | 10 | 2023-02-24 | 3 | 30% | 400000 | 110000
Crux | Task 5 | Thor | 2023-02-09 | 7 | 2023-02-17 | 2 | 28.57% | 320000 | 100000
Crux | Task 6 | Felipe | 2023-02-05 | 7 | 2023-02-14 | 4 | 57.14% | 150000 | 80000
Crux | Task 7 | Karyn | 2023-02-13 | 5 | 2023-02-17 | 1 | 20% | 100000 | 18000
Phoenix | Task 1 | Andy | 2023-02-12 | 7 | 2023-02-21 | 2 | 28.57% | 50000 | 15000
Phoenix | Task 2 | Lucas | 2023-02-22 | 5 | 2023-02-28 | 2 | 40% | 160000 | 60000
Phoenix | Task 3 | Thor | 2023-02-16 | 7 | 2023-02-24 | 3 | 42.86% | 280000 | 140000
Phoenix | Task 4 | Felipe | 2023-02-12 | 7 | 2023-02-21 | 5 | 71.43% | 480000 | 305000
Phoenix | Task 5 | Karyn | 2023-02-15 | 5 | 2023-02-21 | 2 | 40% | 100000 | 35000
Phoenix | Task 6 | Andy | 2023-02-19 | 5 | 2023-02-24 | 2 | 40% | 120000 | 50000
Phoenix | Task 7 | Lucas | 2023-02-25 | 2 | 2023-02-28 | 1 | 50% | 50000 | 25000
Phoenix | Task 8 | Thor | 2023-02-22 | 5 | 2023-02-28 | 3 | 60% | 100000 | 55000
Formulas:
End Date = WORKDAY.INTL(Table2[[#This Row],[Start Date]]-1,Table2[[#This Row],[Duration]],1)